## Tracker
Task | Phase | Category | Owner | Days from start | Due date | Status | Done on | Notes
Confirm the offer, start date, schedule and manager | Before day one | Paperwork | Hiring manager | -14 |  | Not started |  | Start date goes on the Setup sheet
Order the laptop, phone and other equipment | Before day one | Equipment and accounts | IT | -14 |  | Not started |  | Allow shipping time for a remote hire
Send the I-9 instructions and Lists of Acceptable Documents | Before day one | Paperwork | HR | -10 |  | Not started |  | The employer must make both available to new hires (USCIS)
Invite the new hire to complete I-9 Section 1 | Before day one | Paperwork | New hire | -7 |  | Not started |  | Can be done any time after the offer is accepted; due no later than the first day of employment
Send Form W-4 | Before day one | Paperwork | HR | -7 |  | Not started |  | Payroll needs it to withhold federal income tax correctly
Prepare the desk or ship the remote kit | Before day one | Workspace | Hiring manager | -5 |  | Not started
Plan the first-day agenda and the first week | Before day one | Training | Hiring manager | -5 |  | Not started
Assign a buddy | Before day one | Introductions | Hiring manager | -5 |  | Not started |  | Put the buddy's name on the Setup sheet
Create email and system accounts | Before day one | Equipment and accounts | IT | -3 |  | Not started
Send the welcome email: time, place or login, and the I-9 documents to bring | Before day one | Introductions | Hiring manager | -3 |  | Not started
Tell the team who is joining and when | Before day one | Introductions | Hiring manager | -2 |  | Not started
Confirm I-9 Section 1 is complete and signed | Day one | Paperwork | HR | 0 |  | Not started |  | Due no later than the first day of employment
Examine the original I-9 documents: one List A, or one List B plus one List C | Day one | Paperwork | HR | 0 |  | Not started |  | Physically examine them, or use an alternative procedure authorized by DHS and tick its box in Section 2
Collect Form W-4 if it is not back yet | Day one | Paperwork | HR | 0 |  | Not started
Hand over equipment and test every login | Day one | Equipment and accounts | IT | 0 |  | Not started
Give a tour or a walkthrough of the tools | Day one | Workspace | Buddy | 0 |  | Not started
Introduce the team | Day one | Introductions | Hiring manager | 0 |  | Not started
Review the role, hours and who to ask for what | Day one | Training | Hiring manager | 0 |  | Not started
Show where required workplace notices are posted | Day one | Paperwork | HR | 0 |  | Not started |  | DOL's elaws Poster Advisor shows which federal posters apply; state posters come from the state labor department
Hold an end-of-day one-on-one | Day one | Check-ins | Hiring manager | 0 |  | Not started
Schedule role training | Week one | Training | Hiring manager | 1 |  | Not started
Enter the payroll record and direct deposit | Week one | Paperwork | HR | 2 |  | Not started
Give a first small assignment | Week one | Training | Hiring manager | 2 |  | Not started
Complete I-9 Section 2 if it was not done on day one | Week one | Paperwork | HR | 3 |  | Not started |  | Due within 3 business days after the first day of employment; count business days and fix this date if it lands on a weekend
Meet key colleagues outside the team | Week one | Introductions | Buddy | 3 |  | Not started
Collect the policy and handbook acknowledgment | Week one | Paperwork | HR | 4 |  | Not started
Hold the end-of-week check-in | Week one | Check-ins | Hiring manager | 4 |  | Not started
Agree goals for days 30, 60 and 90 | First 30 days | Check-ins | Hiring manager | 10 |  | Not started
File the state new-hire report | First 30 days | Paperwork | HR | 20 |  | Not started |  | Federal law: within 20 days of hire, to the state where the employee works; some states require it sooner, so lower this number if yours does
Finish core training | First 30 days | Training | New hire | 25 |  | Not started
Hold the 30-day check-in with feedback both ways | First 30 days | Check-ins | Hiring manager | 30 |  | Not started
Confirm system access is right and remove what is not needed | First 30 days | Equipment and accounts | IT | 30 |  | Not started
Move to independent work on the agreed goals | Days 31-60 | Training | Hiring manager | 45 |  | Not started
Adjust the training plan | Days 31-60 | Training | Hiring manager | 45 |  | Not started
Ask the new hire for onboarding feedback | Days 31-60 | Check-ins | HR | 50 |  | Not started
Hold the 60-day check-in against the goals | Days 31-60 | Check-ins | Hiring manager | 60 |  | Not started
Note the reverification date if work authorization expires | Days 61-90 | Paperwork | HR | 80 |  | Not started |  | Only if Section 1 shows an expiration date; you may remind the employee at least 90 days before it
Hold the 90-day review | Days 61-90 | Check-ins | Hiring manager | 90 |  | Not started
Set development goals for the next quarter | Days 61-90 | Training | Hiring manager | 90 |  | Not started
Mark every row Done or Not needed and close the tracker | Days 61-90 | Check-ins | HR | 90 |  | Not started

## Setup
Field | Entry
Employee name | Jordan Rivera (sample)
Role | Customer Support Associate (sample)
Start date | 2026-11-16
Hiring manager | Sam Patel (sample)
HR contact
IT contact
Buddy

## Instructions
Step | What to do
1 | Save a copy of this workbook for each new hire and name it after the hire.
2 | On the Setup sheet, replace the sample values with the employee's name, role, start date (cell B4) and the names of the hiring manager, HR contact, IT contact and buddy. Every Due date on the Tracker sheet is the start date plus Days from start.
3 | On the Tracker sheet, set Status to Not needed for rows that do not apply, and add rows for tasks specific to the role. A new row gets its Due date as soon as Days from start is filled in.
4 | Check the I-9 Section 2 row: count 3 business days from the start date and change Days from start if the date lands on a weekend. Lower the state new-hire report row if your state sets a shorter window.
5 | At each check-in, filter by Owner and Status, update Status and fill in Done on. Close the tracker at day 90 when every row is Done or Not needed.
Rule | Form I-9 Section 1: the employee completes and signs it no later than the first day of employment. Source: https://www.uscis.gov/i-9-central/completing-form-i-9/completing-section-1-employee-information-and-attestation
Rule | Form I-9 Section 2: the employer completes it within 3 business days after the employee's first day of employment. Source: https://www.uscis.gov/sites/default/files/document/forms/i-9instr.pdf
Rule | State new-hire report: federal law requires it within 20 days of hire, to the state where the employee works; some states require it sooner. Source: https://acf.gov/css/employers/employer-responsibilities/new-hire-reporting
Rule | Form W-4: the IRS page states no deadline; collect it before the first payroll so withholding is right. Source: https://www.irs.gov/forms-pubs/about-form-w-4
Rule | Workplace posters: requirements vary by statute; the DOL elaws Poster Advisor shows which federal posters apply. Source: https://www.dol.gov/general/topics/posters
Note | Deadlines read on official pages on 2026-11-01. Check your state's rules before you rely on them.